## Overview
CONSTRACK — PROGRESS REPORT
Generated: 2026-06-05 ¦ Run ID: 665f1c2d3e4f5a6b7c8d9e0f ¦ Alignment: HIGH ¦ Forecast: 2026-08-15
|  | 65.5% | 6 | 2026-08-15 | HIGH
|  | Overall Progress | Active Zones | Est. Completion | Alignment
Run Metadata
Run ID | 665f1c2d3e4f5a6b7c8d9e0f
T1 Scan | scan_early_2026
T2 Scan | scan_later_2026
Alignment | HIGH
Forecast | 2026-08-15
Generated | 2026-06-05
Volume Summary
Initial Volume (T1 Scan) | 150.45 | m³
Current Volume (T2 Scan) | 120.15 | m³
Net Volume Change (ΔV) | -30.3 | m³

## Zone Progress
ZONE PROGRESS & STATUS
Zone | Type | Target % | Progress % | ΔVol (m³) | Status | Gap
North Wing | Structure | 72% | 80% | -20.1 | On Track | 8%
South Block | Foundation | 45% | 45.2% | -10.2 | On Track | 0.2%
East Corridor | Frame | 60% | 68% | -5.8 | On Track | 8%
West Annex | Structure | 55% | 58.5% | -7.4 | On Track | 3.5%
Central Hub | Interior | 30% | 35% | -3.2 | On Track | 5%
Roof Section A | Roofing | 88% | 91% | -8.6 | On Track | 3%
AVERAGE

## Timeline & Work Rate
TIMELINE & WORK RATE ANALYTICS
Weekly & Cumulative Progress
Week | Planned % | Actual % | Cum. Planned | Cum. Actual
W1 | 6% | 5.2% | 6% | 5.2%
W2 | 7% | 6.8% | 13% | 12%
W3 | 8% | 7.1% | 21% | 19.1%
W4 | 9% | 8.4% | 30% | 27.5%
W5 | 10% | 9% | 40% | 36.5%
W6 | 11% | 10.2% | 51% | 46.7%
W7 | 12% | 11.5% | 63% | 58.2%
W8 | 13% | 12.3% | 76% | 65.5%
TOTAL/AVG
Schedule Gap Analysis
Week | Planned | Actual | Gap | Gap %
W1 | 6% | 5.2% | -0.8%
W2 | 13% | 12% | -1%
W3 | 21% | 19.1% | -1.9%
W4 | 30% | 27.5% | -2.5%
W5 | 40% | 36.5% | -3.5%
W6 | 51% | 46.7% | -4.3%
W7 | 63% | 58.2% | -4.8%
W8 | 76% | 65.5% | -10.5%

## Volume Heatmap
VOLUME CHANGE HEATMAP (m³) — ZONES × WEEKS
Zone / Week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
North Wing | -5.3 | -0.7 | -2.6 | -2.2 | -6 | -5.6 | -7.2 | -1.2
South Block | -3.7 | -0.7 | -2.1 | -4.3 | -0.7 | -2 | -5.4 | -4.6
East Corridor | -2.2 | -4.9 | -6.6 | -0.5 | -6.5 | -5.7 | -3.1 | -1.7
West Annex | -7.7 | -3 | -1.2 | -1.2 | -6.9 | -5 | -6.6 | -6
Central Hub | -4.5 | -7.8 | -3.3 | -4.6 | -6.7 | -5.1 | -7 | -4.8
Roof Section A | -2.3 | -1.7 | -1.7 | -1.4 | -1.5 | -2.9 | -2.3 | -2.2
TOTAL
Color Scale: Red = Low Activity (-8 m³) → Green = High Activity (0 m³)